## Sheet1
When Pigs Fly TODO
Task | Estimated Hours Left | Hours worked on | Priority (1 - 10) | Condition | N | Not Started
Losing state | 1 | 4 | 10 | S | D | Done
Proper enemie-player collision | 3 | 8 | 9 | S | S | Started
Point tracking | 3 | 0 | 9 | N
Incoming enemies | 10 | 0 | 8 | N
Personal highscore tracking | 6 | 0 | 8 | N
Parallax Manager | 6 | 0 | 6 | N
Credits Menu | ? | 0 | 5 | N
Main Menu | 12 | 0 | 5 | N
Sound effects | ? | 0 | 4 | N
More Parallax Art | 30 | 5 | 4 | S
Slowmo on close collision | ? | 0 | 1 | N
Multiple enemies | 0 | 12 | 10 | D
Powerups | ? | 0 | 1 | N

## Sheet2
Next Milestone | Date : Feb 14th
Must Contain | Current Condition
Losing state | S
Point tracking | S
Highscore tracking | N
Multiple enemies | D
Incoming enemie message | N
Proper enemie collision | N